## Stage 2
Week | Start Time | End Time | Task | Proceeding
1 | 2014-10-13 | 2014-10-20 | - Get request from JP head - Planning for phase 2 -Tutorial for game: + Show information about Enemy in game. + Show information about Tower in game. + Guide when start game. + Guide new icons in game (effect slow, effect burn, ...) - Add map for game (4, 5, 6, 7, 8, 9, 10) - Balance for game | - Tutorial for game complete -Complete 10 map
2 | 2014-10-20 | 2014-10-27 | - Improve Tower for game: + Animation (idle, atack, builde, destroy, level up …) (if team has artist) + Add attributes for tower (Ice, Fire, Black, Light, ...) + Search images for new tower + Add Tower for game + Coding and integrated into game - Items for Tower: + Up attack speed tower + Up attack range tower + Up tower's atk + Up tower's explosion + Up all tower's attributes - Effect when add item for tower - Play and balance for game | 100%
3 | 2014-10-27 | 2014-11-03 | - Skill for tower: + Animation for skill - Improve Enemy for game + Add attributes Enemy (Fire, Ice, Thunder, Blizzard, Earth, Robot, Black, Light, …) + Enemy can attack tower (or hero) + Coding + Calculator in game - Fix error and demo game with new attributes | 100%
4 | 2014-11-03 | 2014-11-10 | - Daily request for game - Archiment for game | - Daily request complete - Archiment complete 90%
5 | 2014-11-10 | 2014-11-17 | - Hero for game + Search (or design image) hero for game + Attributes for hero + Caculator 'Current rank' and 'Nature rank' + Animation for hero + Coding hero in game - Balance for game | 100%
6 | 2014-11-17 | 2014-11-24 | - Hero for game + Enemy die, add experience for hero + Hero die, use diamond or heart revival - House for hero + Search (design image) house for hero + Coding house hero + Integrated into play game - Fix error and demo
7 | 2014-11-24 | 2014-12-01 | - House for game + Design graphics + House sollider - Balance for game - Fix error for game
8 | 2014-12-01 | 2014-12-08 | - Shop for hero + Create scene shop for hero + Weapon for hero + Armor for hero + Medicine for hero + Integrated into game play - Balance for game and fix error. - Demo game
9 | 2014-12-08 | 2014-12-15 | - Child hero + Design graphics + Coding for child hero + Integrated into game play
| 2014-12-15 | 2014-12-22 | - Bluetooth Game
11 | 2014-12-22 | 2014-12-29 | - Online game + Create server for game + port from offline to online
12 | 2014-12-29 | 2015-01-05 | - Online game + Update to server for game + 2 Player + Fix error online game - Demo player online
Formulas:
Start Time = [End Time, row above]
End Time = [Start Time]+7